## Slide 1: SCALLOP/INF1 analysis
https://github.com/jinghuazhao/INF
8/3/2019

## Slide 2: A brief summary (29/11/18)
It is still at a very early stage of the analysis.
Results from INTERVAL and benchmarks from meta-analysis were reassuring.
This was based on stricter criteria on –ld-r2 of the PLINK –clump procedure which was somewhat hampered is its inability to handle small p-value.
It is worthwhile to explore approaches.
There will be further effort on the meta-analysis QC.

## Slide 3: On next steps (29/11/18)
KORA individual level data analysis will be conducted centrally.
Additional studies such as COMBINE will be added.
For cohorts contributing results on PLINK, information such as effect allele (frequency), imputation quality is recommended on a per-cohort basis via qctool as noted in SCALLOP_INF_I_analysis_plan.md.
The QC will be refined and downstream analysis strengthened -- the experiments were based on 1000Genomes extracted from LocusZoom 1.4 at tryggve when there was issues with the up-/down-load. A more desirable reference panel would be INTERVAL, UKBiobank, both involving HRC+UK10K. Finemapping is set to involve PLINK, GCTA, finemap, and JAM, among others.

## Slide 4: Updates I
29 chromosomes remain to be analysed for KORA + ARTN reanalysing at TRYGGVE (smaller size). normalised level ~ age+sex+PC1-5+genotype under additive model with SNPTEST.
BioFinder, MadCam and RECOMBINE were available – these were from Anders beside STANLEY lah1/swe6 with qctool –snp-stats pending while MadCam has RSQ_IMP.
NSPHS has PLINK results but no qctool -snp-stats (in touch with Åsa Johansson on 21/2).
The number of problematic proteins was reduced from 22 to three, IFN.gamma, IL.22.RA1 and TSLP and then none with MAF set to MAF>0.1 for STABILITY (N=2,951), second to INTERVAL (N=4,996).

## Slide 5: Updates II
STANLEY added to meta-snalysis when per-SNP sample sizes are available from study description (results from PLINK dosage analysis, with INFO but no N).
INFO from qctool –snp-stats was added to INTERVAL.
Side projects: R/gap, FM-pipeline, EWAS-fusion, etc. updated and results from FM-pipeline but pending on validation.
INF1.paper.docx at INF/doc as placeholder for paper draft; cohort description needs to be added – an Excel spreadsheet was made available from the (updated) analysis plan and comments are welcome to consolidate.

## Slide 6: Next steps
Cohort-level QC, esp. MAF and INFO score.
Meta-analysis for all cohorts (leaving out RECOMBINE?), including Q-Q/Manhattan/forest/LocusZoom/chord plots – with cis/trans regions when appropriate.
To corroborate PLINK –clump with GCTA –cojo-slct.
Replication?
Downstream analysis, e.g., phenoscanner, MR, GSEA/pathway.

## Slide 7: Manhattan plots

## Slide 8: Q-Q plot